## Checklist
Tractor Recommissioning Checklist
For a tractor that has sat unused for years. Work top to bottom — order matters.
Make / Model |  |  |  | Progress
Gas or Diesel |  |  |  | Done | 0
Hour meter |  |  |  | Total | 28
Date started |  |  |  | Complete | 0%
How to use: fill the yellow cells. Set Done to Yes / No / N/A from the dropdown (N/A for steps that don't apply to your fuel type). Example: Done = Yes, Date = 9/26/2026, Notes = "Sediment bowl had rust flakes".
# | Phase | Task | Why / Caution | Done | Date | Notes
1 | 1. Inspect | Check for rodent nests: air cleaner, intake, exhaust, wiring harness | Chewed wiring is common after long storage
2 | 1. Inspect | Cover exhaust stack if uncapped; check for water or rust inside | Water down the stack can rust a valve or cylinder
3 | 1. Inspect | Inspect tires; inflate or replace | Check for dry rot and sidewall cracks
4 | 2. Fuel | Drain fuel tank completely | Old gas varnishes; old diesel grows algae and holds water
5 | 2. Fuel | Clean sediment bowl and screen
6 | 2. Fuel | Replace fuel filters
7 | 2. Fuel | Inspect fuel lines; replace any cracked or soft lines
8 | 2. Fuel | Gas: clean or rebuild carburetor | Rebuild kit usually needed after 10 years
9 | 2. Fuel | Diesel: bleed air from fuel system per manual
10 | 3. Fluids | Drain engine oil; check for milky oil or water | Milky oil suggests coolant leak
11 | 3. Fluids | Refill engine oil and replace oil filter
12 | 3. Fluids | Check coolant level and condition
13 | 3. Fluids | Inspect radiator hoses and water pump seal | Hoses often crack; pump seals dry out
14 | 3. Fluids | Check transmission/hydraulic fluid; drain a little from plug to check for water | Water settles to the bottom
15 | 4. Free Engine | Remove spark plugs (gas) or injectors/glow plugs (diesel)
16 | 4. Free Engine | Add ~1 tsp oil or Marvel Mystery Oil to each cylinder; soak overnight
17 | 4. Free Engine | Turn crank by hand with breaker bar | If stuck: do NOT force or use starter. Keep soaking and rocking
18 | 5. Oil Pressure | Install fresh, fully charged battery
19 | 5. Oil Pressure | Clean battery cables and terminals
20 | 5. Oil Pressure | With plugs out, crank in 10-15 sec bursts until oil pressure gauge moves | Lubricates bearings before load
21 | 6. First Start | Install new spark plugs (gas) or reinstall injectors (diesel)
22 | 6. First Start | Check points and condenser if equipped
23 | 6. First Start | Start and idle low; confirm oil pressure within seconds | Shut down immediately if no pressure
24 | 6. First Start | Watch for leaks, temperature, and smoke | Some blue smoke early is normal as rings free up
25 | 7. After Running | Run briefly, then change oil again | Flushes sludge picked up on first run
26 | 7. After Running | Test brakes | Before any load
27 | 7. After Running | Test clutch
28 | 7. After Running | Test PTO